## Slide 1: From founder-taught classes to a bridal academy that can run without her
Growth strategy, admissions engine and staged investment plan, 2026–2029
Growth strategy and investment case for PNA, Chandigarh · Prepared for the founder · October 2026
DRAFT FOR DISCUSSION
Gate D recommendation, revised after independent review (Gate E: approve with conditions). 16 October 2026.
Every number carries an evidence label:
VERIFIED
CLAIM
FOUNDER
ESTIMATE
HYPOTHESIS
RECOMMENDATION
Note: Every PNA-specific number is an assumption until the founder's records are supplied (D1). Financials ex-GST, planning case G1 at M9.
Notes: This deck answers six questions in order: how big the opportunity is, what we found, what PNA should do, why, what it takes, and what happens next. Everything is labelled by evidence strength. The final slide is a decision list, not a thank-you.

## Slide 2: Build one Chandigarh Flagship, prove it before pricing it, fund it in tranches
EXECUTIVE SUMMARY · 1 OF 2
One academy, proof first, price second, money released only against evidence.
Source: recommended_strategy.md §1 (1–7), §4.4; economics §1A (peak cash ₹25.2L), §1A.2 (downside) Note: ₹ lakh, Year 1 = Nov 2026–Oct 2027, planning case G1 at M9.
SIX RECOMMENDATIONS
RECOMMENDATION
1
Build one trainer-delivered, small-batch (≤12) bridal-specialist Chandigarh Flagship with a published course ladder, a counsellor-run WhatsApp funnel and published alumni outcomes.
2
First rupee buys proof and response discipline, not advertising.
3
Raise the flagship price only after proof, in two steps (₹75k list → ₹90k list; ₹80k realised).
HYPOTHESIS
planning prices
4
Plan ₹25L, authorise ₹35L, be ready to lose ₹33L.
ESTIMATE
model output
5
Someone other than the founder runs it (Admissions & Operations Lead, month 1).
6
Second engine: out-of-town "Destination" students, piloted Aug–Sep 2027, scaled only at gate G2.
WHAT WE ARE NOT DOING
×
Beauty-services marketplace
×
Owned Delhi NCR or Ludhiana centre
×
Franchising now
×
National online course now
×
₹50L plan in Year 1
Each is rejected on numbers, not taste: see slide 10.
Notes: The independent review confirmed the direction and corrected three things: the money, the gate timing and who owns execution. This slide states the corrected recommendation. The next slide shows what it earns, costs and can lose, so the founder sees the whole shape before any detail.

## Slide 3: Year 1 breaks roughly even before her salary; Year 3 pays only if gates pass
EXECUTIVE SUMMARY · 2 OF 2
₹60.6L revenue and −₹2.8L EBITDA in Year 1; ₹162.9L and ₹39.3L in Year 3 only with every gate passed; cash back in month 29.
Source: Economics §1A (planning table), §1A.3 (Year-3 decomposition), §1A.4 (Payback_IRR), §1B row 21 (₹10L plan); recommended_strategy.md §1 (8, 10) Note: ₹ lakh ex-GST; Year 1 Nov 2026–Oct 2027; Year 3 FY to Oct 2029; planning case G1 at M9.
Evidence:
ESTIMATE
Planning case (Staged_G1M9): G1 passed July 2027, all later gates passed
Y1 revenue
₹60.6L
Nov 2026–Oct 2027
Y1 EBITDA before founder salary
−₹2.8L
−₹11.8L after founder salary
Career enrolments, Y1
81
L2 + L3 new students
Peak cash
₹25.2L
M9, the fit-out month
Y3 revenue, all gates
₹162.9L
₹108.8L base business
Payback before / after salary
M29 / M40
IRR to M36: 46% / −10%
THE FOUNDER'S CHOICE (DECISION D2)
RECOMMENDATION
Boutique
₹10L plan at Base rates
ESTIMATE
₹39.8L revenue, +₹10.8L EBITDA, peak cash ₹3.1L, ~52 career students, founder keeps teaching
Institution
₹35L authorised
ESTIMATE
−₹12L after salary in Year 1, cash back Year 3, a bet on ₹90k pricing and out-of-town demand
vs
Notes: The honest shape of the institution path is a three-year payback on a key-person business with a lease, in exchange for a business that can run without the founder. Year 3 is a gated number, not a forecast: a third of it depends on a price step and a regional engine that are not yet evidenced. The founder must choose between the boutique and the institution with these numbers in front of her (decision D2 on slide 24). Detail: Year-1 EBITDA is −₹2.8L before founder salary and −₹11.8L after ₹75k/month. Year 3: ₹162.9L / ₹39.3L, but ₹54.1L (33%) sits behind price step 2 and gate G2; without them ₹108.8L and roughly zero EBITDA. Payback M29 before her salary, M40 after.

## Slide 4: PNA today is a studio with classes on the side, and every number is unverified
OPPORTUNITY · WHERE PNA STARTS
Fewer than 60 students a year, unknown fees, founder does everything, digital footprint not verifiable from our tools.
Source: assumptions_register.md CA-01, CA-02, CA-03, CA-04, CA-07; chandigarh_competitors.md §2.1–2.4 (S-LC-01/02/07/51/56); economics §1 note (illustrative revenue), §1C #5 (today's share) Note: ₹ per year, 2026. Footprint: VERIFIED as an absence in our searches, tool-limited (CLAIM for site contents).
WHAT WE FOUND
SO WHAT
Founder verifies the real footprint on day 0 (D9)
Business
CLAIM
Bridal/hair studio, Sector 8 Inner Market, with "on demand" pro makeup classes as a side line.
Build the academy as its own business; the studio stays a separate P&L and the practice engine.
Volume
FOUNDER
<60 paying students a year; founder-stated, not yet verified.
Too small for an outcomes record yet; proof has to be built cohort by cohort.
Fee
HYPOTHESIS
ESTIMATE
Not supplied; modelled at ₹60k incl. kit vs a local diploma band of ₹35–75k.
Publish today's fee first; raise it only after proof.
Illustrative revenue
ESTIMATE
₹19.6L quoted (₹16.6L ex-GST), not reported. About 7% of tricity makeup-led learners, illustrative (3–12%).
Everything downstream is a plan for a hypothetical academy until the data pull (D1).
Digital footprint
VERIFIED
ESTIMATE
Website only; no rating, Instagram, reviews or listings found by our tools (Instagram/Maps/Justdial blocked; site refused our proxy). Maturity 3.0/10, provisional.
Tool-limited finding: if a real following or rating exists, the proof timeline and price path move earlier.
Founder dependency
FOUNDER
Founder ≈100% of teaching, counselling and brand; wants to step back within 24–36 months. Investment appetite ₹10–50L.
Hire an execution owner and a Lead Trainer; pace the step-back by evidence, not the calendar.
Notes: We never saw PNA's own records, and our tools could not open Instagram, Google Maps or Justdial, so the "invisible" finding is tool-limited and must be checked by phone and app before the first meeting. If the founder has a real following or a strong Google rating, the proof timeline and price path move earlier. Everything downstream is a plan for a hypothetical academy until the data pull (D1) lands.

## Slide 5: India's paid makeup training is ~₹388 cr; a Chandigarh academy can serve ~₹7.8 cr
OPPORTUNITY · MARKET SIZE
TAM ₹388 cr → SAM core ₹7.8 cr → PNA Year-3 SOM ₹1.88 cr (22% of SAM core); the education market, never the ₹76,141 cr beauty sector.
Source: market_opportunity.md §2 rows 1–9, §3 tree; economics §1B rows 1–9 (sizing TAM_India, Tricity_Recon, SAM_North, SOM_PNA); S-IND-01 Note: ₹ cr per year, run-rate, quoted fees (GST-inclusive); SOM = FY ending Oct 2029. SAM-5 low end 0.75 per economics §1B row 7.
TAM · INDIA
India paid makeup-led tuition
₹388 cr
Range ₹80–1,373 cr · ≈56,800 learners (20,100–126,000)
No published figure exists; our bottom-up build from two methods. The tricity is ₹3.27 cr (≈730 learners), 0.84% of India.
ESTIMATE
SAM CORE · NORTH
Serviceable by a Chandigarh academy
₹7.8 cr
Range ₹2.3–24.2 cr
SAM-1 Tricity: ₹3.3 cr (1.5–5.3, ≈730 learners)
SAM-2 Regional destination: ₹1.9 cr (0.2–10.6)
SAM-3 Hybrid beyond reach: ₹1.4 cr (0.2–5.8)
SAM-4 Working-artist CPD: ₹1.2 cr (0.4–2.5)
ESTIMATE
SOM · PNA YEAR 3
PNA Year-3 training revenue
₹1.88 cr
Range ₹0.41–3.83 cr, incl. GST, all gates passed
22% of SAM core; 13% of tricity learners; ≈20% of the professional tier (reviewer estimate; model line pending).
ESTIMATE
+ Online/short-course layer ₹22.5 cr (3–120): shown beside the TAM, not in it
SAM-5 Online layer ₹7.9 cr (0.75–54): deferred, out of plan
Today, illustrative, NOT actual: ≈₹0.20 cr
Beauty & Salon sector ₹76,141 cr (2025P): context only, ~200x the education TAM. Never the market for this plan.
VERIFIED
Notes: The 17x width of the India band comes from unobserved fee mix and the share of beauty learners who choose makeup, not from learner counts. The tricity number replaces the research file's ₹5.7 cr, which counted makeup and beauty-artistry learners together. The SOM is a plan output checked against the market for plausibility, not a share-of-market assumption.

## Slide 6: Chandigarh is enough to start, not to finish; capacity and visibility bind first
OPPORTUNITY · TRICITY DEMAND
15–25% of the tricity supports a ₹0.5–0.8 cr centre; by Year 3 the plan sits at about 20% of the professional tier (reviewer estimate; model line pending), so growth must come from students who travel.
Source: recommended_strategy.md §3 Q1–Q2, §4.5 H1–H2; market_opportunity.md §7; economics §1A (seat capacity), §2; S-CHD-06/11/18/20; S-IND-01 Note: ₹ cr per year; seat-fit = planning case 2027. ≈20% tier share: reviewer estimate, model line pending (economics §1A.8).
ESTIMATE
Tricity makeup-led market, ₹ cr/yr
≈730 learners at Base (484–879)
Chart: 
| Low | Base | High
Tricity market | 1.45 | 3.27 | 5.28
One-centre take at 15–25% share ≈ ₹0.5–0.8 cr
By Year 3 the plan reaches 13% of all tricity learners and ≈20% of the professional tier (reviewer estimate; model line pending), at ≈1.8x the tricity average fee: H1 binds unless out-of-town students arrive.
Destination hub: plausible, unproven; test it for almost nothing
FOR
VERIFIED
Female higher-education GER 75.4 (Chandigarh) vs 28.5 (India)
ESTIMATE
Four-state pool of women 17–35 is 26x the tricity
VERIFIED
NSDP per capita: Chandigarh 2.28x India
AGAINST
VERIFIED
No origin data for beauty students
VERIFIED
PG ₹8–17.5k/month; 1 of 11 sampled PG listings girls-only
VERIFIED
"No centre nearby" a top barrier nationally
VERIFIED
Punjab 1.03x India income
Studio seats, planning case 2027: share of demand that fits
May 78%
Jun 67%
Jul 77%
Sep 94%
For 12–18 months, seats, visibility and founder hours bind first, not market size.
ESTIMATE
Notes: The tricity is a strong, affluent base and a plausible destination hub, but too small to be the whole story at the plan's fee. The cheap test is to tag every lead by city from month 1 and run a six-student Destination pilot in the August–September 2027 intakes; regional spend waits for gate G2. In the first year the binding constraints are seats in the studio, visibility and the founder's hours, not market size.

## Slide 7: Aspiring artists pay the bills, working artists make the profit, families decide
OPPORTUNITY · SEGMENTS
S1 (18–25 aspiring pros) is core revenue; S3 (working artists) is the profit flywheel; S7 out-of-town and S2 switchers are the growth bets; parents and spouses are the decision unit.
Source: positioning_and_segments.md §1–§2; customer_segments.md §1 (2–3, 7), §3.3; admissions_funnel.md §1 (2), §3; S-CUS-45; S-CHD-12 Note: Prices in ₹, 2026 listings. Segment priorities and routes: RECOMMENDATION.
Evidence:
RECOMMENDATION
segment priorities and routes
Segment | Role | Lead product → next | Primary route | Evidence note
S1 Aspiring professional MUAs 18–25, tricity | Core | L3 Pro → L4 → L5 | CTWA/Search → counsellor <5 min → parent visit → EMI | Highest ticket and LTV
S3 Working artists / salon staff | Flywheel | L4 → L5 | Content → WhatsApp Community → self-serve launch | Profit, repeat purchase, future trainers
S7 Out-of-town overlay (Punjab, HP, Haryana, J&K) | Growth bet | L3 Destination | Search/regional CTWA → online parents' session → video counselling | Main lever past the tricity cap; unproven (H2)
S2 Career-switchers / homemakers 25–40 | Growth bet | L1 Taster → L3 Flex/L2 | ₹999 paid taster → same-day counselling with spouse | Volume; needs a flexible format
S5 Self-makeup learners | Top-of-funnel | Self-Makeup Workshop | Seasonal Reels → instant booking | Seasonal cash
S6 Creators | Top-of-funnel | L4 Camera Makeup | Direct outreach → collab content | Reach
S4 Government-scheme skilling | Defer | None | None | B2G model, compliance-heavy
DECISION UNIT
Parents and spouses
VERIFIED
35%
of students name parents as their main advisor
HYPOTHESIS
≥70%
of S1 cases: parents/spouses approve and pay
VERIFIED
₹14–45k
per function, tricity bridal MUAs (median ₹25k)
CLAIM
₹1.2–6.2 LPA
salaried MUA pay: the ROI anchor families ask about
VERIFIED
No public data on time to first paid booking
Notes: The segment order is about where proof and profit come from, not just size. S3 matters beyond its revenue: working artists are the warm audience for masterclasses and the pool from which PNA's trainers will come. Parents are treated as a decision unit with their own message track, because they hold the veto on the high-ticket course.

## Slide 8: Chains sell breadth and certificates; nobody publishes fees or outcomes
FINDINGS · COMPETITIVE LANDSCAPE
Five tiers compete for the same student; counsellor-led conversion with EMI is universal; fee opacity and "100% placement" claims are the norm.
Source: recommended_strategy.md §3 Q3; chandigarh_competitors.md §1, §6; national_competitors.md §1, §5.1; S-LC-08..23, S-LC-13, S-LC-27..34; S-NC-01/02/04/07/09/13/15/17/22/26; S-BM-08 Note: ₹ list prices, 2024–2026, GST treatment as published. Centre counts and franchise fees self-reported (CLAIM).
Who | What they sell | How they acquire | Published price anchors
Sector 34A cluster: Orane, Lakmé ×2, VLCC, Zuri, Cassia | Broad cosmetology, certificates, "100% placement" | Lead form → counsellor → free demo → EMI | Local 3–6-month diploma ₹35–75k ESTIMATE
Founder-led peers: Nav Brar, Tanvi KG | Small batches, short pro courses | WhatsApp-first, visible proof | Proof, not price: Tanvi KG 4.9/125 CLAIM
Government diplomas: MCM DAV, HMV | 12-month diplomas | Admissions cycle | ₹3,730–35,000 VERIFIED
National chains: Lakmé 140+, Orane 110+, VLCC 106+ centres (self-reported) | Makeup courses; franchises | Counsellor-led, EMI partners, city microsites | ₹35k–1.5L; Lakmé ₹1.3–1.5L; franchise ₹30–60L CLAIM
Premium: Daniel Bauer, Pearl | Access, placements, brand halo | Published prices, campus tours | DBA ₹2.25–5.95L ex GST; Pearl ₹4.45L incl. GST VERIFIED
Online: Orane Online, AAFT | Micro-courses, online diplomas | Celebrity masterclass funnels | ₹499 masterclass → ₹80k diploma CLAIM
Price ladder, ₹ list price (log scale)
₹1k
₹10k
₹1L
T0 digital
₹499–2,999
T1 short module
₹35k–50k
Local 3–6-month diploma
₹35k–75k
T2 core programme
₹80k–1.5L
T3 premium
₹2.25–5.95L
VERIFIED
Only Zuri publishes a fee ladder locally; 4 of 10 nationally
VERIFIED
"100% placement" asserted by VLCC, Orane, Jawed Habib, Meribindiya with no cohort data
VERIFIED
Orane Chandigarh is CIDESCO-listed (IN543); 0% EMI via Bajaj/LoanTap/SaveIN
Notes: Every serious player runs the same machine: a lead form, a counsellor, a demo and financing, with discount anchoring on top. What none of them does is publish fees with inclusions or cohort outcomes. That is the gap PNA can occupy, and the next slide says how, and why it is only a head start, not a moat.

## Slide 9: Published fees, verifiable outcomes and small batches in a working studio
FINDINGS · WHITE SPACE
PNA's white space is contestable in a week on fees, but a working bridal studio and an outcomes record cannot be copied quickly, so proof comes before price.
Source: recommended_strategy.md §3 Q3, Q5; positioning_and_segments.md §3.1–3.2, §4.2, §5; chandigarh_competitors.md §7; S-LC-13; S-NC §5.4, §6 Note: 2026. Studio capacity to host live practice: CLAIM, unverified. Do not compete on discount depth, copy unverifiable credentials, or promise placement or income.
POSITION
The small-batch bridal makeup academy inside a working bridal studio. Students learn the PNA Method on real faces, assist on real bridal bookings in season and leave with a portfolio.
WHAT THE MARKET DOES
WHAT PNA WILL DO
VERIFIED
Hidden fees: only Zuri publishes a fee ladder locally.
RECOMMENDATION
Publish the ladder with all-in cost, EMI and refund terms.
VERIFIED
"100% placement" everywhere, with no cohort data.
RECOMMENDATION
Alumni Outcomes Report: n, dates, % with a paid booking ≤90 days.
CLAIM
Classroom institutes: breadth over bridal depth (chain hours 120–260 h).
HYPOTHESIS
≤12-seat batches, ~280–300 practice hours, live brides.
CLAIM
Founder-led peers sell proof they can show.
RECOMMENDATION
Trainers made visible (PNA Certified Educator); founder hours stated per course.
CONTESTABLE A chain can publish a fee ladder in a week.
NOT QUICKLY COPYABLE A working bridal studio and an outcomes record.
Notes: The positioning is deliberately the opposite of the Sector 34A institutes: depth not breadth, proof not claims, a stated batch cap and stated founder hours. The weak point is that the proof does not exist yet in any form we could verify. Every claim marked "build" stays off the advertising until the asset exists, which is why the first 90 days are about proof, not reach. Trust moves from the founder to three owned assets: the PNA Method, PNA Certified Educators, published PNA Alumni outcomes. Keep the founder's name as masterbrand.

## Slide 10: The integrated flagship scores highest under every weighting; five options are rejected
RECOMMENDATION · OPTIONS
Flagship + destination learning ranks first (3.85 / 3.90 / 3.85); marketplace, owned NCR or Ludhiana centre, franchising and the ₹50L plan fail.
Source: business_model_evaluation.md §4 scorecard, §6.4; recommended_strategy.md §3 Q4, §4.4; economics §3 #9, §5 #5, #8 (BM_Unit_Economics, Plan50L_BaseRates); S-INT-11/12/25; S-CHD-12/22; S-NC-07; S-BM-08 Note: ₹ lakh per year at Base rates, directional. Scores: HYPOTHESIS (judgements on thin evidence).
Option
HYPOTHESIS
Base-
weighted
Growth-
weighted
Founder-
weighted
Knock-
out
Integrated primary
flagship + hybrid layer + masterclasses + studio + alumni desk + credential
3.85
3.90
3.85
G Regional destination + pop-ups
3.55
3.70
3.55
A Chandigarh flagship alone
3.75
3.65
3.80
D Hybrid layer
3.70
3.75
3.70
F1 Masterclasses (component, small ceiling)
4.10
3.80
4.15
Baseline status quo
2.95
2.60
2.90
KO-2
B4 Franchise now
2.60
2.80
2.55
C Pure digital
2.55
2.75
2.50
H Franchisee of a chain
2.45
2.55
2.40
KO-1
B1 Owned tricity satellite
2.40
2.35
2.45
B2 Owned Ludhiana
2.25
2.45
2.15
borderline KO-1
I Government-scheme
1.90
2.00
1.90
B3 Owned Delhi NCR
1.70
2.40
1.40
KO-1, KO-2
E Marketplace
1.65
1.90
1.60
KO-1, KO-2
Scored 1–5 on fit, capital, execution risk, margin, right to win, market, CAC and time. KO-1 capital fit, KO-2 founder goal (applied before scoring). Tinted: recommended.
Why not
Marketplace
ESTIMATE
VERIFIED
−₹932/booking, LTV/CAC 0.35; Urban Company ~10 years to positive adjusted EBITDA, 22.75% of services revenue on onboarding; Blow LTD liquidated
Owned NCR
VERIFIED
rent 3.5x (₹167 vs ₹47/sq ft), same ₹25k bridal median, brand unknown
Owned Ludhiana now
ESTIMATE
≈₹29L fixed cost, −₹7.4L at 46 students, break-even 62 (11–21% of local paid learners) in a chain-served city
Chain franchisee
CLAIM
₹30–60L + 15%+ royalty, erases the founder brand
₹50L plan
ESTIMATE
₹99.3L revenue but −₹3.0L EBITDA and ₹44.2L cash
Launching at ₹90k in month 1
ESTIMATE
no proof, conversion ±20% is worth ₹12.6L
Notes: Small components like masterclasses score highest, which is expected: they are cheap and founder-aligned but have a small ceiling, so they are parts of the primary model rather than engines. Among models that can carry the business, the integrated flagship ranks first under all three weightings, and every physical-expansion, pure-digital, marketplace and government option stays in the bottom half. The rejections are rejected on numbers, not taste. Also from the model: a franchise earns ≈₹2L a year per unit after support; destination students and a partner satellite are positive at small scale.

## Slide 11: One flagship, built as an institution: PNA Method, certified educators, published outcomes
RECOMMENDATION · THE MODEL
A trainer-delivered, ≤12-seat bridal academy in the founder's studio, sold through a published ladder and closed by a counsellor at a parent visit.
Source: recommended_strategy.md §4.1–4.2, §6.1, §6.4, §1 (6); positioning_and_segments.md §4.2–4.3; economics §1A (Destination pilot, A-ECO-161) Note: Months M1 = Nov 2026. Pilot size 6 and format durations: HYPOTHESIS (programme design).
ENGINE 1 · CHANDIGARH FLAGSHIP
RECOMMENDATION
Published ladder: L1 Taster → L2 Foundation → L3 Pro (Weekday / Flex / Destination) → L4 Masterclasses → L5 Pro Circle
The PNA Method
Codified curriculum; PNA Certified Educators
Counsellor funnel + EMI
WhatsApp funnel; closed at a parent visit
Studio practicum
Live-bride practice (separate P&L)
≤12 batches
Trainer-delivered, bridal-specialist
Published outcomes
Outcomes Report; fees and hours public
ENGINE 2 · REGIONAL DESTINATION (AFTER G2)
RECOMMENDATION
HYPOTHESIS
4 weeks live-online pre-work + 5–6 weeks in Chandigarh; vetted women-only stays; parents' orientation; pop-up circuit. Six-student pilot Aug–Sep 2027, scaled at G2.
BRAND ARCHITECTURE
Priyanka Nanda Makeup Academy
→
The PNA Method · PNA Certified Educator · PNA Alumni / "Find a PNA Artist" · PNA Pro Circle
Sister business: Priyanka Nanda Studio
Founder share of contact hours
Ceiling at each month
RECOMMENDATION
Chart: 
| M6 | M12 | M18 | M24 | M36
Founder share | 50 | 40 | 30 | 15 | 10
Each step conditional on trainer parity
Notes: The Business Model workstream called this the "Hybrid Chandigarh Flagship"; we renamed it because in Year 1 the hybrid element is a feature, not the model, and the recorded library waits for Year 2. The studio stays a separate business: it is the academy's proof and practice engine and the default source of the founder's income in Year 1, not an academy revenue line. The step-back is paced by evidence that trainer-led cohorts match founder-led ones, not by the calendar. Takeaway: a Destination format is the second engine.

## Slide 12: Pull students to Chandigarh before opening anywhere; sites only when evidence demands
RECOMMENDATION · GEOGRAPHY AND GATES
Flagship → destination learning (G2) → partner-hosted Ludhiana satellite (G3a) → licensing (G3b); no owned centre and no NCR in three years.
Source: geographic_expansion.md §0–§2, §4.1, §6; recommended_strategy.md §4.2–4.3, §6.2, §7.1; economics §3 #9; S-CHD-01/06/12/13/22 Note: ₹ lakh per year at Base rates, directional. Feeder roles: RECOMMENDATION on ESTIMATE pools.
G1
Stage 1 · Flagship, M0–18
G0 Jan 2027 → G1 end-Jul 2027
Two cohorts ≥6 of 8 studio stations
Trainer parity within 0.3/5
Cash ≤₹15L
G2
Stage 2a · Regional Destination Engine
G2 Jan–Apr 2028
Utilisation ≥75% for 2 quarters
Out-of-town ≥20% of QLs and ≥15% of enrolments before regional spend
Destination pilot completion ≥85%
G3a
Stage 2b · Partner-hosted Ludhiana satellite
G3a ≥ Oct 2028
Utilisation ≥85% for 6 months, waitlist ≥15%
One city ≥25% of out-of-town enrolments
Trainer bench ≥4
G3b
Stage 3 · National reach / licensing
G3b ≥ M30–36
One non-Chandigarh site 12 months without founder teaching
NPS ≥50
Royalty economics positive at ≥3 units
CENTRE VS DESTINATION, LUDHIANA, DIRECTIONAL
ESTIMATE
VERIFIED
Owned centre
Fixed cost ≈₹29L/yr; −₹7.4L at 46 students; break-even 62
Destination student
Contribution positive at small scale, no new rent while flagship seats are spare
Owned vs destination
Owned wins only above ≈69 local students when 10 would have travelled
Partner satellite
Needs more than 2.4x the destination number (N_dest)
Delhi NCR
7.4x the pool but rent 3.5x, same ₹25k bridal median: online/hybrid only
RECOMMENDATION
Stages and gate thresholds
Lowered bar, disclosed. The station-based fill test (≥6 of 8 in the studio; ≥9 of 12 after the move) is a lower bar than the original ≥75%-of-12 test, which no run meets in Year 1; the 8-weekly calendar's effect on revenue timing is not yet modelled.
Notes: The order follows cost and reversibility: fix visibility and response first, grow regionally without fixed cost, add a site only when one city shows demand that converts but is blocked by distance. The empirical question is how much a local site lifts enrolment; only a lift of about 2.4x justifies a partner site and about 3x an owned one. The reference point is Mao Geping, which took 24 years to reach nine campuses. Feeder roles: Ludhiana (priority feeder, first satellite candidate), Jalandhar, Amritsar (hybrid), Patiala and Ambala (commuters), Shimla/Solan (seasonal), Jammu (online only).

## Slide 13: A published five-step ladder, with the flagship price raised only after proof
RECOMMENDATION · PROGRAMME LADDER
₹999 taster → ₹39,900 Foundation → L3 Pro (today's fee → ₹75k list → ₹90k list; ₹80k realised) → ₹10k masterclasses → ₹9,999 Pro Circle; credits carry upward; kit optional.
Source: recommended_strategy.md §6.1, §7.2; positioning_and_segments.md §6; economics §1C #6 (all-in cost); A-GRO-04..09; A-ECO-160/170 Note: ₹, GST-inclusive as shown to families; 2027 calendar. Anchors: local band ₹35–75k; Lakmé ₹1.3–1.5L; AAFT ₹80k (ESTIMATE / CLAIM).
Evidence:
HYPOTHESIS
all prices (planning prices)
RECOMMENDATION
credit rules, gating, kit optional
ESTIMATE
all-in costs
Code | Product | Format / duration | Planning price | Credit rule
L0 | Free layer: Reels, Community, monthly Parents & Students Info Session | Ongoing | Free | —
L1 | Career Taster "A Day at PNA" | 3 h | ₹999 | Credited 100% to L2/L3 within 30 days
L1-S5 | Self-Makeup Workshop | 2 × 3 h | ₹4,999 | —
L2 | Foundation | 4 weeks, ~80 h | ₹39,900 | Credited 100% to L3 within 6 months
L3 | Professional Bridal Makeup Artist Programme | ~280–300 h: Weekday 12 weeks, Flex ~20 weeks, Destination 4 + 5–6 weeks | Current fee → ₹75,000 list (M10) → ₹90,000 list (M16); ₹80k realised; pro kit optional ₹18–25k | One curriculum, three formats
L4 | Masterclasses | 1–4 days | ₹4,999–19,999 (avg ₹10,000) | —
L5 | PNA Pro Circle | Annual | ₹9,999 | Free first year for L3 graduates
Real faces. Real bridal studio. Real portfolio.
ESTIMATE
What a family pays, all-in
₹ lakh, tricity resident; Destination at step 2
Chart: 
| Today (fee incl. kit) | Step 1 (no kit) | Step 2 (no kit) | Step 2 (with kit) | Destination (no kit) | Destination (with kit)
All-in cost | 0.67 | 0.82 | 0.97 | 1.17 | 1.13 | 1.33
PRICE STEPS ARE GATED
Step 1 needs the first Outcomes Report (n≥30), ≥30 reviews at ≥4.5, portfolio gallery and published hours.
Step 2 needs a second report and step-1 conversion held within −15%.
Notes: Price is the biggest lever in the model and the least tested: the plan assumes no loss of demand at a 45% higher all-in cost, and we have no willingness-to-pay evidence yet. That is why the price rises in two steps tied to proof, with a rollback rule if conversion falls more than 20% after a step, and why the V3 interviews now include a price-ladder question at ₹60k, ₹75k and ₹90k. The ladder itself is a hypothesis to publish and test, not a fact. Families see the all-in cost on every fee page.

## Slide 14: WhatsApp is the rail; a counsellor closes career courses at a parent visit within days
RECOMMENDATION · ADMISSIONS FUNNEL
Ten career enrolments a month need ≈143 leads → 66 qualified → 38 counselled → 12 applied → 10 enrolled, with a first human reply inside five minutes.
Source: admissions_funnel.md §1, §3–§5.1, §8.2, §10.1 (Funnel_Base); economics §1B row 25 (Speed_to_Lead); recommended_strategy.md §3 Q6, §4.5 H6–H7; S-CUS-14/20 [CLAIM] Note: Per month, steady state after G1, Base rates. Organic/referral +60% uplift: HYPOTHESIS (unevidenced, RT-08).
STAGE
STEADY-STATE MONTH AT BASE RATES
ESTIMATE
Lead
Meta click-to-WhatsApp or Google Search
143
Meta CTWA 56.8
Paid Search 28.9
Organic 39.9
Referral/walk-in 8.0
Taster 9.4
HYPOTHESIS
Qualified lead
4-question WhatsApp Flow
65.9
Counselled / demo
Visit with a parent, or ₹999 taster
37.8
Applied (token)
₹5,000 token
12.2
Enrolled
No-cost EMI (PNA bears 3–7%)
10.0
Completed
9.0
Advocate
Reviews and referrals
≈4.1 reviews/month
SERVICE STANDARD
RECOMMENDATION
Instant auto-reply ≤1 min
First human reply median <5 min, P90 <30 min
≥90% contacted within 1 h
≥5 touches in 14 days
Counselling booked within 48 h
Parent present at ≥60% of S1 visits
Masterclasses and self-makeup are self-serve. The website is the trust hub, not the closer. The founder is never the inbox. Refund and transfer policy published.
Missing the 5-minute standard costs ≈₹32k/month of extra media for the same enrolments, or −2.3 enrolments (model output of a vendor benchmark; untested).
ESTIMATE
CLAIM
Notes: The hypothesis that WhatsApp beats a website-first funnel is right but incomplete: WhatsApp captures and nurtures, but a high-ticket course is closed at a visit with the parent in the room. Speed-to-lead discipline costs nothing, so it stays, but the "1.5x media" benefit is the output of a vendor benchmark we have not tested; the January–March SLA pilot decides. The organic and referral lines are the least evidenced part of this funnel and are re-based in February on real CRM data.

## Slide 15: A proof flywheel, run in four phases, with paid media capped until gates pass
RECOMMENDATION · GROWTH ENGINE
Student work becomes content, content brings WhatsApp leads, a counsellor converts them, graduates produce proof; media ≤₹15k/month to G0, ≤₹60k to G1.
Source: growth_marketing_strategy.md §0, §1.1–1.2, §9; execution/marketing_channel_plan.md §3.2; recommended_strategy.md §3 Q6, §6.3; economics §1A (T1 media) Note: ₹ thousand per month, Nov 2026–Oct 2027, planning case. Seasonality index: HYPOTHESIS (A-GRO-40; wedding-season dates VERIFIED, S-CUS-13).
Proof flywheel
Student work & outcomes
Content + small paid push
WhatsApp leads, counsellor converts
Portfolios, reviews, referrals
Five spend gates, green four weeks running before media rises
SG1 tracking · SG2 follow-up discipline · SG3 capacity · SG4 unit economics · SG5 product proof
Steady-state route mix target: CTWA 30% · Search 20% · Organic 20% · Referral 20% · Taster 10%
Year 1: growth & marketing ₹26.7L, of which paid media ₹7.0L
RECOMMENDATION
HYPOTHESIS
ESTIMATE
Paid-media cap, ₹ thousand per month, planning case (= ₹7.0L Year 1)
ESTIMATE
Paid-media cap, ₹k/month
Chart: 
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Paid-media cap | 15 | 15 | 40 | 50 | 60 | 60 | 60 | 60 | 60 | 80 | 100 | 100
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
G0 15 Jan
SG + KT-1a 5 Mar
G1 26 Jul
Phase
0
1 Test & Prove
2 Scale the flagship
3 Extend
Career-enquiry index
0.80
0.75
0.70
0.80
0.90
1.00
1.30
1.35
1.25
1.10
1.05
1.00
Founder availability
Low
High
Medium–Low
Ramp from M10: founder decision at G1
Each gate turning amber freezes increases; red rolls spend back to the last green level. Phase 3 (Aug–Oct): Destination pilot, two pop-up pilots ≤₹2L, ≤₹1L online masterclass pilot.
Notes: Timing matters: it is mid-October, the wedding season starts now and fills the founder's calendar, so November to February is for foundations, real-bride content and masterclasses in the lean months, with paid tests from January. In the planning case the media ramp lands on the August–October pre-season window and the May–July student peak runs at test-level spend; that is the cost of waiting for evidence. Each gate turning amber freezes increases; red rolls spend back to the last green level. The Q4 ramp to ₹1.0L/month is not pre-approved: at G1 the founder decides whether to accept the planning case's 53% fully loaded reading (red) or take the ₹70k/month option. Phases: 0 Foundations (19 Oct–22 Nov 2026) · 1 Test & Prove (to 28 Feb 2027; tests T1–T8 from G0; Outcomes Report by 31 Jan) · 2 Scale the flagship (Mar–Jul, inside the T1 cap) · 3 Extend (Aug–Oct).

## Slide 16: One WhatsApp inbox, one lead record, enforced reply timers, conversions fed back to ads
RECOMMENDATION · WEBSITE, CRM AND ANALYTICS
A minimum stack at ≈₹18–20k/month (BSP + CRM + GA4/CAPI + payment links) that makes the funnel visible and the SLA enforceable; no LMS until Year 2.
Source: execution/technology_and_crm_requirements.md §1, §4, §8, §9.1, §11; growth_marketing_strategy.md §4.1, §9 SG1–SG2; S-GRO-02/04/05/06/08/12 Note: ₹ per month incl. 18% GST where applicable, 2026 list prices. Run-rates: ESTIMATE from vendor list prices (CLAIM).
Entry points
CTWA ads, Search ads
Google Business Profile, Instagram
Website: trust hub, five core pages (L3, L2, Fees & EMI, For Parents, Student Work); ₹1.2L rebuild
Walk-in, referral codes
WhatsApp BSP
WhatsApp Business API from day 1
Flow asks: course, start month, city, parent involved
Multi-agent inbox; CTWA attribution
1–2 tracked numbers
CRM (3 seats)
One lead record per person
Lead → QL → Counselled → Applied → Enrolled → Completed → Advocate
SLA timers; lost-reason codes
Razorpay links and an EMI partner
Outputs
CAPI / offline conversions back to Meta and Google
GA4 + GTM + Looker Studio weekly one-pager
Accounts reconciliation ±5%
RECOMMENDATION
MONTHLY RUN-RATE, ₹
ESTIMATE
₹10L plan
≈8,000
₹30L plan
≈19,800
₹50L plan
≈35,900
WEEKLY ONE-PAGER
RECOMMENDATION
Leads by source
Lead→QL by route
First-response median and P90
% contacted ≤1 h
Visits with parent present
Cost per QL/enrolment by route
Lost-reason Pareto
Batch fill
Reviews
SG1–SG5 and G0/G1 status
ATTRIBUTION RULES
First touch drives CAC by route; last touch before QL drives optimisation. The CRM, not the ad platform, is the source of truth (reconciles with accounts ±5%; ≥95% of leads tagged).
Notes: A small academy does not need an enterprise CRM; it needs one inbox, one record per person, timers that make the five-minute standard visible, and conversion events sent back to the ad platforms so paid media optimises on qualified leads and enrolments rather than clicks. Buy only what spend gates SG1 and SG2 require. The recorded pre-work library and LMS wait for Year 2; the Destination pilot runs its pre-work live online.

## Slide 17: Route-level media buys an enrolment for ≈₹5.9k; the budget we plan costs ≈₹11.7k
ECONOMICS · CHANNEL FUNNEL
₹35k/month buys ten enrolments at Base rates; the plan spends ₹1.0L/month, reconciled by a calibration factor (2.42); the cost range is ~9x wide.
Source: admissions_funnel.md §10.1–10.2 (Funnel_Base, funnel Summary); economics §1A (gate metrics), §1A.7 (A-ECO-51), §3 #4, #7; marketing_channel_plan.md §1 (3), §3.1; recommended_strategy.md §3 Q6 Note: ₹ per steady-state month after G1; Year-1 months 7–12 for the gate KPIs. Route values ESTIMATE from HYPOTHESIS inputs.
BY ROUTE, BASE MONTH
ESTIMATE
HYPOTHESIS
Route | Leads | Cost per QL | Media CAC per enrolment
Meta CTWA | 56.8 | ₹750 | ₹5,682
Paid Search | 28.9 | ₹1,111 | ₹7,234
Organic | 39.9 | — | ₹0 media (fixed content cost)
Referral | 8.0 | — | ₹3,000 reward
Taster | 9.4 tickets | ₹400 | ₹3,752 (≈ −₹5.6k net of tickets)
Total | 143 | — | ₹5,878 (6 paid)
The planned ₹1.0L/month is ≈1.9x what the route maths needs (₹37.6k); the gap is awareness, retargeting and brand spend, reconciled in the model by A-ECO-51 = 2.42, not by evidence.
Months 7–12: effective media CAC ₹11.7k (SG4 amber); fully loaded acquisition 53% of career revenue (red).
The Q4 ramp is not pre-approved: at G1 the founder accepts the 53% reading or a ₹70k/month steady state (≈7 fewer enrolments, −₹0.5L EBITDA).
ESTIMATE
Media CAC per paid enrolment, ₹ thousand, same 10 enrolments
Chart: 
| Aggressive | Base | Conservative
Media CAC | 2.1 | 5.9 | 18.5
Planning case effective CAC | 11.7 | 11.7 | 11.7
Planning case effective CAC ₹11.7k (× 2.42 calibration)
SG4 bands: green ≤9k · amber 9–12k · red >12k
Base: 143 leads, ₹35,265 media + ₹6,000 rewards, ₹5,878. Conservative: ≈257 leads, ≈₹1.1L media, ≈₹18,450. Aggressive: ≈89 leads, ≈₹12.5k, ≈₹2,080.
Steady-state ₹1.0L/month: Meta career CTWA ₹32k · Workshops ₹15k · Masterclass launches ₹8k · Proof & retargeting ₹18k · Google Search ₹22k · Test reserve ₹5k
Notes: This is the slide an investor will push on, so it says the uncomfortable thing first: the two workbooks agree by construction, not evidence, and the Year-1 plan is acquisition-inefficient by design because the growth team is hired ahead of volume to build proof. SG4's 40% line stays the gate; amber means a founder review, not a pass, and green is a Year-2 expectation. The January–March paid tests replace the calibration with measured cost per enrolment.

## Slide 18: At today's fee a batch needs 8 of 12 seats to break even; at ₹90k list, 3.6
ECONOMICS · PROGRAMME UNIT ECONOMICS
Price realisation is the economic hinge: seat contribution rises from ₹22.2k to ₹50.4k across the price path; the business breaks even at ≈7.8 career enrolments a month on the month-12 cost base.
Source: Economics §1B rows 10–14, §1C #2, §1A (break-even, GST), §5 #1, #2, #6; recommended_strategy.md §3 Q7 table Note: ₹ per student / per month, Base rates, ex-GST unless stated. All seat and cohort figures: ESTIMATE (Unit_Economics).
ESTIMATE
L3 seat economics, ₹ thousand per student
Chart: 
| Today ₹60k incl. kit | Step 1 ₹75k list | Step 2 ₹90k list
Contribution before CAC | 22.2 | 39.6 | 50.4
After CAC | 0 | 32 | 42.8
 | Today | Step 1 | Step 2
Realised price | ₹60k incl. kit | ₹66.7k realised | ₹80k realised (₹67.8k ex-GST)
Contribution margin | 44% | — | 74%
Cohort break-even fill | 67% (8 of 12) | 38% | 30% (3.6 of 12)
7.8/month
Break-even career enrolments
ESTIMATE
94/yr at step 1 on the M12 cost base, which carries the second trainer and the Operations Lead. Reference: 5.5/month (66) unstaged Base; 4.4 (52) Conservative.
₹10.9L/yr
GST absorbed vs on top
ESTIMATE
Planning-case swing (₹12.7L at Base). No exemption for private non-recognised training (VERIFIED). A CA opinion is decision D8.
8.0x
Career student LTV:CAC, Base
ESTIMATE
First-course contribution ₹41.8k, 24-month LTV ₹50.5k, blended CAC ₹6.3k (funnel view).
Replacing the founder's unpaid teaching costs ≈₹10L in Year 1 and ₹17–19L a year in Years 2–3, plus ≈₹8L a year for an academy manager from Year 2.
ESTIMATE
Notes: The proof gate is an economic hinge, not a marketing milestone: at today's fee a 12-seat batch needs eight students to cover its trainer and occupancy cost, which is why the business cannot carry salaried trainers without the price step. The founder's unpaid teaching is today's margin; the step-back is affordable only at roughly six or more career enrolments a month after the full price step. A chartered accountant's opinion on GST is worth about ₹11 lakh a year and is decision D8. Step 1: ₹39.6k before CAC, ₹32.0k after; break-even 38%. Step 2 (₹80k realised, ₹67.8k ex-GST): ₹50.4k (74%) / ₹42.8k; break-even 30% (3.6 of 12).

## Slide 19: Plan to need ₹25L, authorise ₹35L, and know the worst case is ₹33–36L
ECONOMICS · SCENARIOS, CASH AND STAGING
Tranche 1 ≤₹15L to a July 2027 gate (₹11.8L expected); Tranche 2 ≤₹15L only on May–July actuals; ₹5L contingency above; three hard rules make the ceiling real.
Source: Economics §1A (planning table, reading 3), §1A.2 (downside, final run Staged_Cons_CutM5_Deep), §1B rows 15–20; recommended_strategy.md §1 (4), §5, §7.3 KT-1a/KT-10, §10 row 32; execution/twelve_month_roadmap.md §4.2–4.3 (monthly cash line, D6b rule) Note: ₹ lakh ex-GST; Year 1 Nov 2026–Oct 2027; cash excludes income tax, GST timing, working capital and founder draw.
ESTIMATE
Year 1 by scenario, ₹ lakh (career enrolments)
Chart: 
| Planning G1 M9 (81) | Upside G1 M6 (91) | Base bundle, ref. (89) | Conservative, ref. (33)
Revenue | 60.6 | 66.7 | 71 | 17.6
EBITDA before founder salary | -2.8 | -0.8 | 6.8 | -13
Peak cash | 25.2 | 26.5 | 24.6 | 14.9
Waiting for G1 until M9 costs ≈10 enrolments, ₹6.2L revenue and ₹2.1L EBITDA vs the M6 upside, lowers peak cash ₹1.3L and adds two months of evidence.
ESTIMATE
Cumulative cash, planning case, ₹ lakh
Chart: 
| Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
Cumulative cash | -3.93 | -5.85 | -9.97 | -11 | -11.71 | -11.8 | -11.43 | -10.84 | -25.18 | -25.06 | -23.79 | -22.54
₹15L T1 cap | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -15 | -15
₹28L KT-11 warning | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28 | -28
₹30L planned | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30 | -30
₹35L authorised | -35 | -35 | -35 | -35 | -35 | -35 | -35 | -35 | -35 | -35 | -35 | -35
₹15L T1 cap
₹28L KT-11 warning
₹30L planned
₹35L authorised
Peak ₹25.2L in Jul (M9, fit-out). Headroom ₹4.8L / ₹9.8L vs ₹30L / ₹35L. If the academy pays the founder ₹75k/month, peak cash is ₹32.6L (M10) and the contingency is consumed.
T1 Prove (M1 → end M9): up to ₹15L; planning use ₹11.8L by M8
T2 Build (M10 → M12): up to ₹15L more; ₹14.7L of space committed in the G1 month (fit-out ₹10.4L, deposit ₹3.1L, stations ₹1.2L)
Contingency: ₹5L (₹35L authorised)
T3 Extend (G2, Year 2): ₹4–10L
T4 Site (G3a): ₹2–5L per partner site
WHAT ₹35L CAN LOSE, CASH BY OCT 2027
ESTIMATE
Funnel fails, nobody acts
₹36.2L
Rising ≈₹2.3L/month; visible Feb 2027
Funnel fails, KT-1a deep cut at the March review (the rule as adopted)
₹25.4L
Still burning ≈₹0.9L/month → revert to the boutique model
False-positive G1, peak season fails after the move
₹32.7L
Visible Sep 2027; exit ₹4.9L (₹3.1L notice + ₹1.8L severance); ₹11.6L sunk, ₹3.1L deposit recoverable
Reference only: shallow cut ₹28.7L; cut only at M10 (old rule) ₹33.9L (full table: A6). Capex + deposits Year 1 ₹17.2L.
THREE HARD RULES
RECOMMENDATION
KT-1a mandatory cut at the March 2027 review
No lease before G1 is green on May–July actuals
KT-10 post-move stop-loss
Notes: The T1 team is the proof engine and includes the execution owner, so we did not shrink it; its burn at adverse rates (about ₹2.3L a month) is governed by a mandatory cut at the March review, not by a smaller team. Even after the deep cut the business still burns about ₹0.9L a month at adverse rates, so a failed Tranche 1 means reverting to the boutique model, not waiting. Once the lease is signed the floor is ₹32–33L; the only protection is reading G1 on actual May–July results, never on a forecast of them. Planning case: ₹60.6L revenue, −₹2.8L EBITDA, 81 enrolments, peak cash ₹25.2L (M9, fit-out month). The T1 cap and KT-1a are read on the academy's cash before any founder draw; the default (D6b) is that the studio pays her.

## Slide 20: A third of Year-3 revenue sits behind gates; cash returns in month 29 before salary
ECONOMICS · THREE-YEAR DIRECTIONAL VIEW
₹162.9L / ₹39.3L in Year 3 with every gate passed; ₹108.8L and roughly zero EBITDA without price step 2 and the regional engine.
Source: Economics §1A (3-year rows), §1A.3, §1A.4, §1B rows 22–23; recommended_strategy.md §1 (8), §3 Q7 ("Year 3 is a gated number"), §7.2 Note: ₹ lakh ex-GST; FY ending Oct 2027/2028/2029; IRR on cash actually drawn (₹25–33L); cash before tax and GST timing.
ESTIMATE
Year-3 revenue, ₹ lakh, planning case: ₹162.9L all gates
₹108.8L base business + ₹54.1L (33%) gated
Chart: 
| Base business | Price step 2 | Destination (G2) | Online (audience gate) | Adjacents
Year-3 revenue | 108.8 | 15.2 | 21 | 11.4 | 6.5
Year-3 EBITDA, base business
−₹0.4L −₹10.9L after salary
Year-3 EBITDA, all gates
₹39.3L ₹28.8L after salary
ESTIMATE
Cumulative cash, end of year, ₹ lakh (before salary)
Chart: 
| Y1 | Y2 | Y3
Cumulative cash | -22.5 | -12.8 | 22.9
Payback M29 (Mar 2029) before salary
M40 (Feb 2030) after salary; after-salary cash at M36: −₹6.3L
₹ lakh | Y1 | Y2 | Y3
Revenue | 60.6 | 113.7 | 162.9
EBITDA before founder salary | −2.8 | 16.3 | 39.3
EBITDA after ₹75k/month salary (+8%/yr) | −11.8 | 6.6 | 28.8
Cumulative cash, end of year | −22.5 | −12.8 | +22.9
ESTIMATE
46% / −10%
IRR to M36, before / after salary
ESTIMATE
87% / 33%
IRR to M60 (Years 4–5 flat, no terminal value)
ESTIMATE
None
Base business only: no payback within 5 years
Step 2 adds ₹14.5L of Year-3 EBITDA at no conversion loss, ₹7.5L at −10%, ₹0.4L at −20%; it stops adding value at ≈21% loss.
Labelled "all gates passed"; the Conservative reference reaches ₹36.7L revenue and −₹9.6L EBITDA in Year 3.
Notes: The deck never shows the ₹163L case alone: the ₹109L base business sits beside it so that the founder and any investor can see how much depends on a price step and a regional engine that are not yet evidenced. Read the IRR as the return on the cash actually drawn, with no terminal value, so it understates a business still growing at month 36. If step 2 and G2 never land, the base business returns nothing within five years on this cost base, and the cost base would have to be re-sized. Takeaway: payback M29 (IRR 46% to M36) before the founder's salary, M40 (−10%) after it.

## Slide 21: Ninety days to see the funnel, answer in minutes, publish proof, start cohort one
EXECUTION · FIRST 90 DAYS (19 OCT 2026 – 17 JAN 2027)
Hire the Operations Lead in November, make the funnel visible, publish fees at today's price, start cohort 1 on 4 January, pass G0 on 15 January.
Source: recommended_strategy.md §3 Q8 (90 days), §7.1 G0, §9.2; execution/first_90_days.md §0, §3, §6, §7; execution/marketing_channel_plan.md §4 Note: ₹ lakh ex-GST, 19 Oct 2026–17 Jan 2027; day 0 = 19 Oct. Cohort 1 ≈3 students (ESTIMATE). Plan, dates, G0 criteria: RECOMMENDATION.
Oct 2026
Nov
Dec
Jan 2027
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
G0 Fri 15 Jan
Decisions & data pull
D1–D9 days 0–10
Ops Lead + CRM/WhatsApp + SLA
Set up
Live day 20 · Ops Lead in post 2 Nov · median reply ≤15 min
GBP + academy Instagram
GBP day 14
Instagram day 34
Website: 5 core pages + fee ladder
Build
Live day 27
Lead Trainer
Search: two finalists
Shadowing from 1 Dec
Co-teach
Proof assets
Portfolio-day shoot; alumni survey day 20
Outcomes Report 31 Jan →
Paid tests
Plumbing test Nov
T3 taster Dec
T1/T2 from 18 Jan
Legal / GST / B&WSSC
CA opinion day 21
B&WSSC enquiry by day 76
G0 PASS CRITERIA (ALL EIGHT)
RECOMMENDATION
Founder data pull complete
CRM + WhatsApp live, ≥95% tagged
Median first reply ≤15 min
Fee ladder, course pages, refund/EMI policy and GBP published
Lead Trainer hired and shadow-teaching
Academy Instagram live
B&WSSC enquiry lodged and CA opinion obtained
Consent forms in use, alumni survey sent
ESTIMATE
90-day new spend ₹11.5L (incl. the Operations Lead at ₹40k/month) plus ₹3.2L running costs; revenue ₹5.5L; net cash −₹9.97L to end-January; T1 high ₹11.8L in April against the ₹15L cap.
Notes: The 90 days build the machine; they do not buy growth. The independent review found thirteen workstreams and about ten hires run by nobody, so the plan now has an owner (the Admissions & Operations Lead, decision D5a, blocking) and a scope cut to the G0 criteria plus the first cohort; SEO pages beyond the first five, YouTube and the second interview wave move to February. The first cohort is expected to under-fill (about three students) and that is planned for. Day 0–7: founder verifies her real footprint (D9), supplies her numbers (D1), posts the Operations Lead role (D5a), claims Google Business Profile, opens the academy Instagram, briefs the Lead Trainer search (two finalists), engages a CA on GST and counsel on the lease checklist. By end-January: B&WSSC enquiry lodged; first Alumni Outcomes Report by 31 January; paid tests ≤₹15k/month until G0.

## Slide 22: Prove in the studio by July, build at G1, run the new academy by October
EXECUTION · TWELVE-MONTH MILESTONES
G0 (15 Jan) → KT-1a cash check (26 Feb) and cut review (5 Mar) → G1 on May–July actuals (26 Jul) → lease, move, second trainer, price step 1 and the media decision (Aug) → Destination pilot (16 Aug, 20 Sep) → Year-1 review (29 Oct).
Source: execution/twelve_month_roadmap.md §0, §1, §3, §3.1, §4.1, §4.3, §5, §7, §9 (re-based to Staged_G1M9); recommended_strategy.md §3 Q8, §7.1 G1, §9.2, §10 row 32; economics §1A.6 Note: Nov 2026–Oct 2027; ₹ lakh ex-GST; hours per month, planning case. Cohorts, hours, cash: ESTIMATE.
2026
2027
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
G0 15 Jan
KT-1a 26 Feb · review 5 Mar
Upside G1 check 30 Apr
G1 26 Jul
Year-1 review 29 Oct
Funding
T1 ≤₹15L
T2 ≤₹15L + ₹5L contingency · T3 prep Oct
L3 cohorts (students)
C1 4 Jan
3.2
C2 1 Mar
5.6
C3 26 Apr
8.7
C4 21 Jun
9.4
C5 16 Aug
9.1
C6 11 Oct
10.1
Team
Ops Lead 2 Nov
Lead Trainer 1 Dec
Retainer senior trainer Feb
Lead Trainer certified 9 Apr
2 Aug: second trainer, second counsellor (0.5 FTE), Assistant #2, front desk; Academy Manager M13
Space
Studio
+ evening slot 6 Mar
Seats bind May–Jul
Move Aug, 12 stations · KT-10 watch
Price
Today's fee
₹75k list from 1 Aug; ₹90k M16
Paid media, ₹k/month
15
15
40
50
60
60
60
60
60
80*
100*
100*
Proof
Outcomes Report 31 Jan
≥30 reviews by 26 Feb
Report #2 Sep
Destination & regional
City tags from M1
Partners Mar–Apr
Pilot 16 Aug + 20 Sep; pop-ups
Founder share / teaching h
92% · 81
83% · 73
75% · 66
67% · 59
58% · 103
50% · 88
48% · 85
47% · 82
45% · 79
43% · 114
42% · 110
40% · 106
Cumulative cash, ₹L
−3.93
−5.85
−9.97
−11.00
−11.71
−11.80
−11.43
−10.84
−25.18
−25.06
−23.79
−22.54
Lowered bar (G1): the station test replaces the original ≥75%-of-12 test, which no run meets in Year 1; revenue timing on the 8-weekly calendar is not yet modelled. * = founder decision at G1.
Notes: The year has one job: prove the flagship on today's studio inside the Tranche-1 budget, then build it out at G1. The old gate test (two cohorts three-quarters full of twelve) is never met in Year 1 on any run, so G1 is now measured against the stations in the room, and the intake calendar runs eight-weekly from March, the only modelled calendar on which the studio cohorts pass and both post-move cohorts reach nine of twelve. The hidden constraint is founder hours, not share: on the planning case her teaching reaches 114 hours in August, and if she exceeds 110 hours for two months running the second trainer is pulled forward or takes more slots. Planning case by quarter: revenue ₹5.5L / ₹13.4L / ₹16.6L / ₹25.0L; EBITDA −₹6.7L / −₹1.0L / +₹1.3L / +₹3.5L; career enrolments 8.0 / 18.7 / 21.9 / 32.4. Intakes: 21 Jun (≈9.4) is the first cohort to meet the station test ≥6 of 8 (M8); 16 Aug ≈9.1 of 12; 11 Oct ≈10.1 of 12. Space: heads of terms Jun–Jul subject to G1; lease, deposit and fit-out in the week of 26 Jul. Destination: partner search Mar, 2–3 partners Apr; pop-ups Ludhiana Sep, Patiala Oct, ≤₹2L.

## Slide 23: Price, the post-move downside and founder load are the risks; seven tests decide them
NEXT STEPS · RISKS AND VALIDATION TESTS
Ten named risks with owners; the paid tests, the willingness-to-pay block, the SLA pilot and the Destination pilot replace the weakest assumptions by mid-2027.
Source: recommended_strategy.md §4.5 (how each hypothesis is tested), §7.3, §8; economics §1A.5 (tornado, named stresses); execution/first_90_days.md §3 (V1–V7, W5–W7); S-CHD-18/20; S-NC-04 Note: ₹ lakh, Year 1, planning case. Risk ranking, mitigations, tests and triggers: RECOMMENDATION; thresholds HYPOTHESIS; tornado ESTIMATE (full version: A5).
#
Risk
Evidence (one figure)
Mitigation
Owner
1
Price realisation fails
₹19.7L Year-1 EBITDA swing; zero elasticity modelled; all-in cost +45%
Two gated steps; KT-5 rollback; WTP block in V3
Founder + Ops Lead
2
Downside after the move
₹14.7L committed on the G1 reading; ≈₹33L if the peak fails
G1 on May–July actuals; ≤3-month notice; KT-10
Founder
3
Downside before the move
₹2.3L/month burn; ≈₹36L with no cut
KT-1a mandatory deep cut in March
Founder + Ops Lead
4
Founder load shifted, not reduced
114 h in August (planning case); 128 h in May if G1 lands at M6
Hours disclosed; >110 h twice pulls trainer 2 forward
Founder
5
Nobody owns execution
Thirteen workstreams and ~10 hires in 90 days
Ops Lead from M1 (D5a); scope cut to G0
Founder → Ops Lead
6
Optimistic funnel benchmarks
9x range; calibration factor; organic flat −₹2.5L; masterclasses half −₹5.9L
Test level until SG1–SG5 green; KT-4
Ops Lead
7
Trainer hire and pay unsupported
₹60k unsourced (HYPOTHESIS)
Two finalists; retainer option; KT-12
Founder + Ops Lead
8
Capacity binds May–July
78% / 67% / 77% of demand fits
Evening slot from March; move at M10
Ops Lead
9
GST, lease, NOC
₹10.9L GST swing (planning case)
CA opinion before fees; ≤3 months' notice
CA + Founder
10
Out-of-town safety; misleading claims
1 of 11 PG listings girls-only; "100% placement" is the norm
Vetted women-only stays; KT-8; no placement promises
Ops Lead + Founder
VALIDATION TESTS
V1 founder data pull (day 10)
V2 enquiry-log audit
V3 15–20 interviews, WTP block at ₹60k / 75k / 90k
V4 alumni survey n≥30 → Outcomes Report 31 Jan
V5 mystery shopping of 6–8 competitors
V6 / T1–T5 matched-budget paid tests Jan–Mar
V7 speed-to-lead pilot Jan–Mar
Destination pilot Aug–Sep: completion ≥85%, pass within 5 points, price ≥90% of Weekday
KILL TRIGGERS
KT-1a March cut · KT-2 two cohorts <5 from 26 Apr · KT-3 trainer parity · KT-5 price rollback if conversion falls >20% · KT-10 post-move exit · KT-12 trainer attrition · KT-13 founder incapacity
ESTIMATE
Year-1 EBITDA swing, ₹ lakh
Chart: 
| Fees | Conv. | GST | Rent | Var. | CPL | Media | Fill
EBITDA swing | 19.7 | 12.6 | 10.9 | 6.5 | 5.1 | 2.5 | 1.1 | 0.7
Notes: The independent review's five decisive assumptions are the price path, the enrolment ramp, the funnel rates, the trainer hire and the gate timing; each now has a test with a date and a trigger that acts on the result. The tornado is run on the recommended plan, not the unstaged Base, so the headroom it shows is the real one: fees 20% low would take peak cash to ₹33.3L, inside the ₹35L authorisation only because the contingency exists. None of these risks is new; what is new is that each has an owner who is not the founder doing the work. Tornado (planning-case Year-1 EBITDA swing, ₹ lakh): fees 19.7 · conversion 12.6 · GST 10.9 · rent 6.5 · variable cost 5.1 · CPL 2.5 · media ±30% 1.1 · cohort fill 0.7.

## Slide 24: Twelve decisions, three of them this week, decide which academy PNA becomes
NEXT STEPS · FOUNDER DECISIONS AND NEXT ACTIONS
Supply the numbers, choose boutique or institution, authorise Tranche 1 with the three hard rules, and hire the execution owner before anything else starts.
Source: recommended_strategy.md §9.1 (D1–D10, D5a, D6a, D6b), §9.2; final/executive_summary.md "Decisions needed"; execution/first_90_days.md §1 (dates) Note: Dates relative to 19 Oct 2026. All items: RECOMMENDATION; figures quoted: ESTIMATE (economics §1A, §1B row 21).
DECISION
BY
DEFAULT IF UNDECIDED
D1
Supply actual enrolments, fees, enquiry log, stations, team costs
day 10
Models run on labelled assumptions
D2
Boutique (₹10L, +₹10.8L/yr, she keeps teaching) or institution (₹35L authorised, −₹12L after salary in Year 1, cash back Year 3)
day 7
Staged plan
D3
Authorise Tranche 1 (≤₹15L) and the ₹30L + ₹5L envelope with the three rules
day 7
—
D4
Studio stays a separate P&L and the practice engine
day 30
Studio continues as Priyanka Nanda Studio
D5
Hire a Lead Trainer at market pay with IP assignment; stop being the inbox
day 7
—
D5a
Hire the Admissions & Operations Lead in November (counsellor pay + ₹15k/month, ₹1.8L/yr)
day 7
None acceptable: nothing else starts
D6 / 6a / 6b
Step-back path, 110-hour rule, Year-1 income: the studio pays her (if the academy pays, peak cash ₹32.6L, contingency consumed)
day 7
Studio pays the founder
D7
Published fees with all-in cost, EMI, refunds; no placement promises
day 24
—
D8
CA on GST; counsel on lease, NOC, key-person cover
opinion day 21
Fees modelled GST-inclusive
D9
Verify the real Instagram, Google and review footprint
day 0
Deck says "not verifiable"
D10
Record franchise and GM appetite
record now
Defer
NEXT ACTIONS, DAYS 0–7
D9 verification call
Founder data pull and enquiry-log audit
Post and fill the Operations Lead role
Claim GBP with the exact signage name and Sector 8 address
Create the academy Instagram
WhatsApp BSP + Phase-0 CRM
Brief the Lead Trainer search (two finalists)
CA engaged on GST, counsel on the lease checklist
Consent forms
Fee page drafted at today's fee with all-in cost
Alumni survey sent
Portfolio-day shoot booked
B&WSSC enquiry sent
What the staged plan buys: find out for about ₹12L whether proof, trainer parity and cohort fill exist before committing ₹14.7L to a lease.
Notes: Nothing in this plan starts until the Operations Lead is hired or the 90-day scope is cut to the G0 criteria plus cohort one; that is why D5a is marked blocking. The founder's day-0 job is a thirty-minute check of her real digital footprint by phone and app, because the "invisible" finding came from tools that could not open Instagram or Maps. We close on decisions, not thanks: the next meeting should open with D1's data and the D2 choice.

## Slide 25: Two methods, one tricity number: ₹3.27 cr, not ₹5.7 cr
APPENDIX A1 · MARKET SIZING METHOD
The India TAM is the mean of a pipeline method and a supply method; the tricity figure reconciles a ₹5.7 cr "makeup + beauty-artistry" estimate down to makeup-led learners only.
Source: market_opportunity.md §3–§6, §8; economics §2; india_market_analysis.md §1, §8; chandigarh_market_analysis.md §1, §8; S-IND-01/02/04/05 Note: ₹ cr per year, quoted fees. Methods and bands: ESTIMATE. "No published figure exists": VERIFIED (negative finding).
DO NOT USE
USE INSTEAD
Tricity ₹5.7 cr / 1,256 students
₹3.27 cr base (₹1.45–5.28), ≈730 learners
India ₹800–1,500 cr
₹388 cr (₹80–1,373 cr)
PNA revenue ₹0.3 cr today
₹19.6L quoted / ₹16.6L ex-GST, illustrative
PNA 4% share today
About 7%, illustrative (3–12%)
Beauty & Salon ₹76,141 cr / products USD 1.5 bn / salon services USD 12.6 bn / wedding spend ₹6.5 lakh cr as the market
Context only: the education TAM is ~0.5% of the beauty-and-salon sector
3 crore jobs by 2030
KPMG 26.3M workforce by 2030; 5.44M incremental training need 2022–30
METHOD
ESTIMATE
Method 1 (pipeline): skill-council certifications → ×unorganised share (~60%) → self-paying share → makeup-led share (15/25/35%) → blended fee across four tiers (₹522 cr alone).
Method 2 (supply): branded centres × learners per centre + independents × makeup share × fee.
Mean ₹388 cr; band ₹80–1,373 cr driven by fee mix and makeup share, not learner counts.
Tricity: top-down ₹2.18 cr; CA-05 restated ₹3.96 cr; supply count ₹3.67 cr → ₹1.45 / 3.27 / 5.28 cr. North five-state slice ₹30 cr (7.65% of incremental training need) is a cross-check only.
KEY FACTS THE SIZING RESTS ON
5.44M incremental training need, 0.68M a year
VERIFIED
~60% unorganised
VERIFIED
Chandigarh 6.16% B&W workforce share
VERIFIED
47% blended, 41% classroom, 90% short courses
VERIFIED
Certification 1.3–2.1 lakh/yr (counters conflict)
CLAIM
Notes: The reconciliation explains 5.76x of the 10.5x learner gap between the two research streams by scope, inflow, workforce intensity and urban concentration; a 1.82x residual is kept as evidence that the tricity is a makeup-academy hot-spot. The scope guardrail matters for credibility: the education TAM is about 0.5% of the beauty-and-salon sector, so quoting the sector would overstate the opportunity about 200 times.

## Slide 26: Two hypotheses hold, four are plausible but unproven, one is strongly supported
APPENDIX A2 · HYPOTHESIS VERDICTS
H1 and H5 are supported; H2, H4, H6, H7 need the tests in the plan; H3 is a constraint more than an asset.
Source: recommended_strategy.md §4.5; business_model_evaluation.md §5; international_benchmarks.md §6.3; S-CHD-11; S-IND-01; S-INT-05/11/12/25; S-CUS-14/20/33 Note: Verdicts: ESTIMATE / HYPOTHESIS as stated per row.
Hypothesis | Verdict | Decisive evidence | Test that settles it
H1 Tricity caps a single centre | Supported; binds at the plan's fee by Year 3 unless out-of-town share is delivered ESTIMATE | ₹3.27 cr; 15–25% ≈ ₹0.5–0.8 cr; ≈20% of the professional tier (reviewer estimate, model line pending) | CRM city tags, mystery shopping
H2 Chandigarh as destination hub | Plausible, unproven HYPOTHESIS | GER inflow (VERIFIED); no beauty-origin data; PG cost/safety | ≥20% out-of-town QLs; two pop-ups ≥8%; six-student pilot
H3 Founder brand = asset and constraint | Constraint strongly supported; asset unverified outside the referral circle ESTIMATE | 100% of delivery; teaching up to 114 h/month on the planning case, 128 on the G1-at-M6 upside; Mao Geping "founder absent" complaint (CLAIM; 9 campuses in 24 years) | Team-led conversion ≥75% of founder-led by G1
H4 Hybrid beats pure online on completion and price | Supported on price for hands-on bridal tiers; completion unproven HYPOTHESIS | Premium tiers offline; 47% prefer blended (VERIFIED); Airblack's 80% completion claim is live-online (CLAIM) | Destination pilot completion ≥85%, practical pass within 5 points, price ≥90%
H5 Marketplace is a different business | Strongly supported VERIFIED | UC ~10 years; Blow liquidated (VERIFIED); LTV/CAC 0.35 | Not expected to change
H6 WhatsApp counselling beats website-first | Right but incomplete HYPOTHESIS | Preference claim is Meta-commissioned (CLAIM); the close is a parent visit or paid taster | T1, T4
H7 Follow-up discipline beats more spend | Plausible, untested HYPOTHESIS | 1.5x media is a model output of A-GRO-24; 5-vs-30-minute study is a 2007 vendor study (CLAIM) | V7 SLA pilot Jan–Mar 2027; SG2 kept because it costs nothing
Notes: The review downgraded H7 from "supported" to "plausible, untested" because its evidence was circular, and re-tagged two headline facts as commissioned surveys. Nothing in the plan depends on H7 being true, because the response-time standard costs nothing. The expensive bets, H2 and the price path, are gated behind pilots that cost almost nothing to run.

## Slide 27: Every gate is measurable from the CRM, attendance and accounts
APPENDIX A3 · GATE DEFINITIONS
G0 instruments the baseline (Jan 2027); SG1–SG5 govern media month to month; G1 (end-Jul 2027) releases Tranche 2 on eight tests; G2 (Jan–Apr 2028) releases the regional engine.
Source: recommended_strategy.md §6.2, §7.1–7.2; growth_marketing_strategy.md §9; economics §1A (gate metrics), §1A.6 Note: Dates 2027–2028. Thresholds: RECOMMENDATION (HYPOTHESIS where numeric). Planning-path cohort sizes and SG4 readings: ESTIMATE.
Gate | Window | Thresholds (as adopted at Gate E) | Unlocks / if missed
G0 | M3, Jan 2027 | Founder data pull and footprint verified; Operations Lead in post; CRM + WhatsApp BSP live, ≥95% of leads source- and city-tagged; median first human reply ≤15 min (≤5 by M6); fee ladder with all-in cost, course pages, refund/EMI policy, GBP published; Lead Trainer hired and shadow-teaching; academy Instagram live; B&WSSC enquiry lodged; CA opinion on GST; consent forms; alumni survey sent | Unlocks paid tests above ₹15k. If missed: media held at ≤₹15k, no trainer hire, weekly review; KT-1 if unmet by M4
SG1 | Weekly from Dec 2026; four green weeks before scaling | ≥95% source tags, CAPI/offline conversions firing, CRM reconciles with accounts ±5% | Amber freezes increases; red rolls back
SG2 | Weekly | Median first reply <5 min, P90 <30 min, ≥90% contacted within 1 h, ≥5 touches in 14 days, lost reasons ≥90% | Amber freezes increases; red rolls back
SG3 | Weekly | Next two batches scheduled with seats ≥ forecast, counsellor ≤30 conversations/day, founder hours within budget | Amber freezes increases; red rolls back
SG4 | Weekly | Media CAC per paid career enrolment ≤₹9k green, ₹9–12k amber, >₹12k red; fully loaded acquisition ≤40% green, 40–50% amber (founder review, not a pass), >50% red. Planning case: ₹11.7k and 53% in M7–M12, the accepted Year-1 inefficiency | Amber freezes increases; red rolls back
SG5 | Weekly | Completion ≥85%, NPS ≥50, ≥30 Google reviews at ≥4.5, outcomes report n≥30, refunds/drops <10% | Amber freezes increases; red rolls back
Notes: The old G1 test could not be passed on the plan's own numbers, so it was restated against the stations in the room and moved to a reading on actual May–July results. Spend gates are separate from stage gates on purpose: media moves week to week on SG1–SG5, while leases, hires and price steps move only on G0–G3b. The SG4 amber band is not a pass; it triggers a founder review.

## Slide 28: Every gate is measurable from the CRM, attendance and accounts, continued (2 of 2)
APPENDIX A3 · GATE DEFINITIONS
Source: recommended_strategy.md §6.2, §7.1–7.2; growth_marketing_strategy.md §9; economics §1A (gate metrics), §1A.6 Note: Dates 2027–2028. Thresholds: RECOMMENDATION (HYPOTHESIS where numeric). Planning-path cohort sizes and SG4 readings: ESTIMATE.
Gate | Window | Thresholds (as adopted at Gate E) | Unlocks / if missed
G1 (1) | Last week of Jul 2027, on May–July actuals | Two consecutive L3 cohorts starting at ≥6 of 8 studio stations (adopted 8-weekly calendar: 26 Apr ≈8.7, 21 Jun ≈9.4; first passable with the 21 Jun cohort, M8); ≥9 of 12 after the move (16 Aug ≈9.1, 11 Oct ≈10.1) | Unlocks Tranche 2. If missed: stay in the studio on T1's cost base, re-review M12, then KT-10b
G1 (2)–(4) | as above | (2) Completion ≥85%, NPS ≥50, ≥40% of completers review on cohorts 1–2. (3) Pooled trainer-led cohorts within 0.3/5 of founder-led; team-led conversion ≥75% of founder-led. (4) SG1–SG3 green 4 weeks; SG4 ≤₹12k with ≥12 cumulative paid enrolments; paid-social lead→enrolment ≥4% | All eight tests must hold
G1 (5)–(8) | as above | (5) Outcomes Report n≥30 with "% paid booking ≤90 days"; ≥30 reviews at ≥4.5. (6) Founder ≤50% of hours. (7) Cumulative cash ≤₹15L. (8) No lease before this reading; ≤3 months' notice, fire NOC, shop-and-establishment clearance | All eight tests must hold
G1 disclosure | — | Test (1) is a lower bar than the original ≥75%-of-12 test, which no run meets in Year 1, and the 8-weekly calendar's effect on revenue timing and trainer hours is not yet modelled | Disclosed (R-7)
G2 | M15–M18 (Jan–Apr 2028) | Utilisation ≥75% for two quarters; out-of-town ≥20% of QLs and ≥15% of enrolments before regional spend; two pop-ups ≥25 paid attendees and ≥8% attendee→enrolment in 60 days, tickets ≥70% of cost; Destination pilot completion ≥85%, practical pass within 5 points, price ≥90% of Weekday; accommodation partners signed, zero serious incidents; trainer bench ≥3; founder ≤30%; flagship EBITDA-positive two quarters; SG4 ≤40% | Unlocks Tranche 3 and price step 2 (only if step-1 conversion held within −15%)
Notes: Continuation of Appendix A3 · Gate definitions. The old G1 test could not be passed on the plan's own numbers, so it was restated against the stations in the room and moved to a reading on actual May–July results. Spend gates are separate from stage gates on purpose: media moves week to week on SG1–SG5, while leases, hires and price steps move only on G0–G3b. The SG4 amber band is not a pass; it triggers a founder review.

## Slide 29: Thirteen triggers say in advance what stops, when, and what it costs
APPENDIX A4 · KILL AND PIVOT TRIGGERS
The money rules (KT-1a, KT-10, KT-11) protect the ₹35L ceiling; the quality rules (KT-2, KT-3, KT-5, KT-7) protect the brand; KT-12/13 cover trainer loss and founder incapacity.
Source: recommended_strategy.md §7.3; economics §1A.2 Note: ₹ lakh, cash by Oct 2027. Triggers: RECOMMENDATION (thresholds HYPOTHESIS); rupee consequences: ESTIMATE (Staged_Cons_CutM5_Deep, _CutM5, _CutM10, Staged_Cons, Staged_FalsePos, Plan10L_BaseRates). Tinted: money rules.
Trigger | Condition | Action and consequence
KT-1 | G0 unmet by Feb 2027 | No media above ₹15k, no trainer hire
KT-1a | March 2027 review: cash ≥₹15L, or paid CAC >₹12k after minimum learning spend, or 1 Mar cohort <4 | Mandatory deep cut to the stop-loss state (paid media paused, content team and freelancers released, Lead Trainer 0.5 FTE, founder-led delivery, Operations Lead kept): modelled ₹25.4L by Oct 2027 vs ₹28.7L shallow / ₹33.9L at M10 / ₹36.2L no cut; team notice ≈₹1.2L
KT-2 | From the 26 Apr cohort, two consecutive cohorts <5 students (cohorts 1–2 exempt) | Freeze fixed costs, review price and response speed
KT-3 | After the first two trainer-led cohorts, NPS >15 points below founder-led or team conversion <60% | Hold founder share ≤50%; the move waits one intake
KT-4 | Cost per QL >2x target or zero QLs after ₹5,000; CAC payback >6 months for two quarters | Kill the cell; cut the channel
KT-5 | QL rate or counselled→applied falls >20% after a price step | Revert for one intake; step 2 not taken if step-1 loss settles above 15%
KT-6 | Pop-up city <15 paid attendees twice or <3% conversion after 3 events | Drop or rotate the city
Notes: The review found the original triggers mis-timed against the plan they policed: KT-2 was half-tripped by the plan's own first cohort, KT-3 fired too late, and the old KT-10 assumed a pivot that is impossible once a lease is signed. The adopted set is ramp-aware before the move and a priced exit after it. KT-11 is a warning line, not a protection; the real protections are KT-1a before the lease and KT-10 after it.

## Slide 30: Thirteen triggers say in advance what stops, when, and what it costs, continued (2 of 2)
APPENDIX A4 · KILL AND PIVOT TRIGGERS
Source: recommended_strategy.md §7.3; economics §1A.2 Note: ₹ lakh, cash by Oct 2027. Triggers: RECOMMENDATION (thresholds HYPOTHESIS); rupee consequences: ESTIMATE (Staged_Cons_CutM5_Deep, _CutM5, _CutM10, Staged_Cons, Staged_FalsePos, Plan10L_BaseRates). Tinted: money rules.
Trigger | Condition | Action and consequence
KT-7 | Destination pre-work completion <70% or practical pass >10 points below | Revert the segment to Weekday
KT-8 | Any serious safety incident | Suspend the partner; independent review
KT-9 | Partner site <60% fill for 2 cohorts | Exit
KT-10 | After the move: contribution <60% of plan for two months, or both first post-move intakes (16 Aug, 11 Oct) start below 60% of planned fill (≈5.5 and ≈6.1 students) | Give lease notice (₹3.1L), release T2 hires (₹1.8L), revert to the studio; ₹11.6L sunk, ₹3.1L deposit recoverable, cash floor ≈₹32–33L
KT-10b | G1 still red at M12, no lease | Boutique path (~52 career students, +₹10.8L EBITDA at Base rates)
KT-11 | Actual cumulative cash reaches ₹28L | Freeze discretionary spend (≈₹1.2L/month); a warning, not protection (committed spend after the move ≈₹4L/month)
KT-12 | Lead Trainer notice or two missed co-teaching weeks | Retainer trainer within two weeks; founder share may rise to ≤60% for one cohort
KT-13 | Founder incapacity ≥4 weeks | Trainers carry cohorts, theory from recordings, no new intake until return
Notes: Continuation of Appendix A4 · Kill and pivot triggers. The review found the original triggers mis-timed against the plan they policed: KT-2 was half-tripped by the plan's own first cohort, KT-3 fired too late, and the old KT-10 assumed a pivot that is impossible once a lease is signed. The adopted set is ramp-aware before the move and a priced exit after it. KT-11 is a warning line, not a protection; the real protections are KT-1a before the lease and KT-10 after it.

## Slide 31: Fees, conversion and GST move Year-1 EBITDA by ₹20L, ₹13L and ₹11L
APPENDIX A5 · SENSITIVITIES
The tornado is run on the recommended plan, not the unstaged Base; any single adverse driver at the tested magnitude breaches the ₹30L planned line but stays inside ₹35L.
Source: Economics §1A.5, §1A.3, §1B row 24 (superseded tornado) Note: ₹ lakh, Year 1 Nov 2026–Oct 2027, planning case. All values: ESTIMATE (Flex_* re-runs on Staged_G1M9; Sensitivity groups 6–8).
ESTIMATE
Swing in Year-1 EBITDA, planning case, ₹ lakh (adverse peak cash)
Chart: 
| Fees ×0.8/×1.15 (₹33.3L) | Conversion ×0.8/×1.2 (₹29.7L) | GST on top vs absorbed (₹19.1L if on top) | Rent ₹130/₹47 per sq ft (₹29.6L) | Variable cost ×1.25/×0.75 (₹27.2L) | CPL ×1.3/×0.7 (₹26.0L) | Media ±30% (₹24.8L / ₹26.2L) | Cohort fill ×0.8/×1.2 (₹25.7L)
EBITDA swing | 19.7 | 12.6 | 10.9 | 6.5 | 5.1 | 2.5 | 1.1 | 0.7
NAMED STRESSES, ONE-SIDED
Masterclass volume at half
−₹5.9L EBITDA, +₹4.2L peak cash
Non-paid engine flat at today's rate
−₹2.5L, −6.9 enrolments
Lead trainer at ₹75k
−₹1.7L
Price response at step 1
−₹0.8L (−10%) / −₹2.0L (−20%)
Step 2 in Year 3
+₹14.5L / +₹7.5L / +₹0.4L at 0 / −10 / −20% conversion
Superseded unstaged-Base tornado, reference only: fees ₹23.0L, conversion ₹15.1L, GST ₹12.7L, rent ₹8.7L.
Notes: Price is the largest and least-tested lever, which is the reason for the two-step path and the willingness-to-pay block in the interviews. The masterclass line is the second-largest unevidenced volume: 153 seats in Year 1 assume a warm working-artist audience that we could not verify, so the ramp is tied to the first masterclass's sell-through in January. The non-paid engine's +60% lift is re-based in February on real CRM counts.

## Slide 32: The founder can be told exactly what each failure path costs and when she would know
APPENDIX A6 · DOWNSIDE RUNS
Five modelled failure paths, their Year-1 EBITDA, peak cash, the month they become visible, and what is sunk versus recoverable.
Source: Economics §1A.2 (final, incl. Staged_Cons_CutM5_Deep); recommended_strategy.md §5 ("What ₹35L can lose"), §10 row 31 Note: ₹ lakh ex-GST; cash by Oct 2027 unless stated. All values ESTIMATE; exit terms (3 months' notice, 1 month severance): HYPOTHESIS (A-ECO-158/159).
Run | What happens | Year-1 EBITDA | Peak cash (month) | Visible | Exit / severance
Staged_Cons | T1 team at Conservative rates, no cut; effective paid CAC ₹40.3k; 5–7 enrolments/month from May; burns ≈₹2.3L/month | −₹32.1L | ₹36.2L (M12, rising) | M4 Feb 2027 | —
Staged_Cons_CutM5_Deep | KT-1a mandatory cut at the March review to the stop-loss state; 2–3 career enrolments/month | −₹22.2L | ₹25.4L (M12), still rising ≈₹0.9L/month; burn does not reach zero in Year 1 | M4 | ₹1.3L
Staged_Cons_CutM5 | Shallow cut to the ₹10L-plan base only | −₹25.2L | ₹28.7L (rising ≈₹1.3L/month) | M4 | ₹1.2L
Staged_Cons_CutM10 | Old rule | −₹30.4L | ₹33.9L | M4 | ₹1.2L
Staged_FalsePos | G1 passed at M9 on a false positive; demand ×0.6 from M10; price reverted M11; exit M12; lease costs ≈₹1.7L/month while held | −₹14.7L | ₹32.7L (M12), flat after exit | M11 Sep 2027 | ₹4.9L (₹3.1L notice + ₹1.8L severance)
Staged_FalsePos_M6 | Upside timing; exit M9 | −₹14.5L | ₹32.4L (M9) | M8 Jun 2027 | ₹4.6L
On a lease exit ₹11.6L of fit-out and stations is sunk; the ₹3.1L deposit is recoverable. Even the deep stop-loss state burns ≈₹0.9L/month at adverse rates (≈₹0.9L contribution against ≈₹1.8L fixed), so the March review must also decide the boutique path for Year 2.
Notes: Three conclusions were adopted: the T1 cap is a hard stop reviewed monthly from February with a mandatory deep cut in March; the ₹10L-plan cost base is not a resting state at adverse rates, so the stop-loss goes deeper and a failed Tranche 1 means reverting to the boutique model; and once Tranche 2 is spent the floor is ₹32–33L, protected only by the pre-lease evidence rule. The ₹28.7L figure belongs to a shallow cut and is not the adopted rule.

## Slide 33: On the adopted 8-weekly calendar the station test is met in June and post-move cohorts fill
APPENDIX A7 · COHORT FILL VS THE G1 TEST
The old "two cohorts ≥75% of 12" test is never met in Year 1; against the stations in the room (a lower bar, disclosed), G1 is first passable with the 21 June cohort (M8).
Source: Economics §1A.6 (final), §1A.8 item 5; recommended_strategy.md §7.1 G1, §10 rows 22, 31–32; execution/twelve_month_roadmap.md §3.1; execution/kpi_framework.md §3 DEL-01 Note: Students per cohort, 2027 intake dates. Cohort sizes: ESTIMATE (Staged_G1M9 section K, A-ECO-164/165); thresholds and calendar: RECOMMENDATION.
ESTIMATE
L3 cohort starts, students (cap 12)
Chart: 
| 4 Jan | 1 Mar | 12 Apr | 26 Apr | 24 May | 21 Jun | 5 Jul | 16 Aug | 27 Sep | 11 Oct
Adopted 8-weekly | 3.2 | 5.6 | 0 | 8.7 | 0 | 9.4 | 0 | 9.1 | 0 | 10.1
6-weekly alternative | 3.2 | 5.6 | 6.3 | 0 | 7.2 | 0 | 6.8 | 6.9 | 7.5 | 0
G1 26 Jul
Studio test ≥6 of 8 stations (to July)
Post-move test ≥9 of 12 (from August)
G1 decision 26 Jul on May–July actuals
Calendar | First passable | M9 achievable? | After the move (≥9 of 12)
8-weekly | 21 Jun (M8) | Yes | Met (9.1, 10.1)
6-weekly | 24 May (M7), confirmed 5 Jul | Yes | Not met (6.9, 7.5)
8-weekly: 4 of 6 cohorts pass. 6-weekly: 3 of 7 pass. The end-July decision is achievable on either calendar.
RECOMMENDATION
Intakes 8-weekly from 1 March 2027 (adopted)
The calendar re-allocates modelled enrolments; revenue timing on it is a deferred model run.
Notes: Cohorts one and two are expected to under-fill and are exempt from the kill trigger. The six-weekly rhythm passes one cohort earlier but leaves the 16 August intake only a six-week enrolment window, so it cannot fill a twelve-station room; any post-move test would then fail on the plan's own path. The calendar changes which cohort a student joins, not how many enrol, so modelled revenue and trainer hours are unchanged until the deferred run. Takeaway: only the 8-weekly calendar also fills a 12-station room after the move.

## Slide 34: The review approved the direction and corrected the money, the gate and the owner
APPENDIX A8 · INDEPENDENT REVIEW
Three critical and twelve major objections; eight conditions; the deck now answers the fourteen questions a sceptical investor asks.
Source: strategy/independent_review.md §1–§2, §5, §7; recommended_strategy.md §10 (arbitration log rows 22–31) Note: Navigation and audit trail. Objection counts: VERIFIED (review §2).
CHANGES ADOPTED
Planning case moved to G1 at M9 with M6 as upside (RT-02)
Downside runs added and the worst loss stated in rupees (RT-01)
An execution owner funded in Tranche 1 (RT-03)
Founder hours disclosed, second trainer in the planning case, cover for attrition and incapacity (RT-04)
Price response and a "no step 2" Year-3 line, payback and IRR (RT-05/10)
Corrected CAC KPI and the calibration stated plainly (RT-06)
SG4 kept at 40% (RT-07)
CA-07 restated as tool-limited (RT-09)
Tier-matched share line (RT-12)
H7 downgraded (RT-13)
Triggers re-timed (RT-14)
Destination pilot moved to Aug–Sep (RT-15)
Investor question | Answered on slide
What does PNA make today? | 4
What is the return on ₹30–35L? | 3, 20
Worst loss and when I would know? | 19, A6
Who runs this? | 11, 24
Why will a family pay ₹90k with no public reviews? | 13, 23
What if Orane/Lakmé/Zuri copy published fees? | 9
Can you hire the trainer? | 23
What if the trainer leaves or the founder is out a month? | A4 (KT-12/13)
How much of Year 3 is gated hope? | 20
Why ₹1.0L/month media when ₹37.6k buys the same? | 17
What does the founder live on? | 24 (D6b)
What is the lease? | 19, A3 (G1 pre-lease rule)
Is the digital invisibility real? | 4, 24 (D9)
Who owns the PNA Method? | 24 (D5), 23
Notes: The arbitration log is kept in the appendix on purpose: every overrule of a workstream recommendation is explained, modelled and traceable. The one question the deck still cannot answer is the first one, what PNA actually makes today, and that is decision D1.

## Slide 35: Every number carries a tag, a source and, where it is still open, a date
APPENDIX A9 · EVIDENCE AND SOURCES
Six evidence labels, one source register, three workbooks with 0 formula errors, and four outstanding model runs that do not change the recommendation.
Source: Economics header, §1A.8, §7; recommended_strategy.md §11.3; research/sources.md header; final/deck_sources.md Note: "0 formula errors": VERIFIED (build log, economics header). F = fetched, S = snippet-only.
EVIDENCE LABELS
VERIFIED
[FACT] sourced and checked
CLAIM
First-party or unverified; never read as verified
FOUNDER
Stated by the founder, not verified
ESTIMATE
[EST] our arithmetic, shown in the workbooks
HYPOTHESIS
[HYP] to be validated
RECOMMENDATION
[REC] a decision, not a model output
SOURCE REGISTER
Prefix | Covers | F / S
S-IND | India market, skill council, KPMG | See register
S-CHD | Chandigarh demographics, rents, PGs | See register
S-NC | National competitors | See register
S-LC | Local competitors, PNA footprint | See register
S-INT | International benchmarks | See register
S-CUS | Customer research | See register
S-BM | Business-model sources | See register
S-GRO | Growth and martech vendors | See register
research/sources.md: all accessed 2026-10-16. Access limits: Instagram, Maps, Justdial, Sulekha blocked; PNA's site refused the proxy.
Workbooks: market_sizing_model.xlsx, funnel_economics.xlsx, business_forecast.xlsx: 0 formula errors; all Checks TRUE. Delivered after Gate E: Staged_Cons_CutM5_Deep (₹25.4L) and the G1 station-test pass month (M7 on 6-weekly, M8 on 8-weekly).
Outstanding model items (no deck number depends on them)
Staged_FalsePos_PhasedFitout: phased fit-out; sunk cost in the false-positive case
Staged_G1M9_Retainer: retainer trainer from M4; four-week founder-incapacity stress
SOM_PNA tier-matched share line: replaces the reviewer's ≈20%
Contingency sensitivity: GST input-credit timing, one-month instalment delay
8-weekly calendar: effect on revenue timing and trainer hours (§1A.8)
Notes: The deck's number discipline is its credibility: one source of numbers, assumption IDs on every input, superseded figures kept in an audit note. The outstanding runs refine the downside and the share test; none of them changes the recommendation, the ask or the gates.